## A
PUBLIC ARCHAEOLOGY LABORATORY
- COST PROPOSAL -
|  | PREPARED FOR | Middleborough Historical Commission
|  | DATE | 2013-09-17
|  | PROJECT | Oliver Estate
|  | SERVICES | Historic and Archaeological Assessment
| PERSONNEL | TASK | HOURS | RATE | COST
| Senior Architectural Historian | Coordination/Meetings | 4 | 100.28 | 401.12
|  | Survey | 6 | 100.28 | 601.68
|  | Inv Form Update/Recomm. | 6 | 100.28 | 601.68
| Architectural Historian | Research | 8 | 73.12 | 584.96
|  | Survey | 6 | 73.12 | 438.72
|  | Inventory Form Update | 24 | 73.12 | 1754.88
| Architectural Assistant | Research | 4 | 45.96 | 183.84
|  | Inventory Form Update | 4 | 45.96 | 183.84
| Principal Investigator | CoordinationMeetings | 2 | 100.28 | 200.56
|  | Field Survey | 6 | 100.28 | 601.68
|  | Archaeology Memo/Recomm. | 6 | 100.28 | 601.68
| Project Archaeologist | Research | 2 | 68.94 | 137.88
|  | Field Survey | 6 | 68.94 | 413.64
|  | Archaeology Memo | 24 | 68.94 | 1654.56
| Technical Editor | Editing | 4 | 73.12 | 292.48
| Production Coordinator | Typing/Formatting | 2 | 66.85 | 133.7
| GIS Specialist | Technical Graphics/Maps | 4 | 66.85 | 267.4
| TOTAL PERSONNEL COSTS |  | 118 |  | 9054.3
| OTHER EXPENSES | DESCRIPTION |  |  | COST
| Reproduction | Report Preparation, Copying & Graphics |  |  | 300
| Photographs | Processing & Prints |  |  | 50
| Communication | Postage |  |  | 35
| Expendable Supplies | Archival Paper, Bags etc. |  |  | 10
| Mileage | 200 | Miles @ $ | 0.51 | 102
| Curation | 1 | Boxes @ $ | 100 | 100
| TOTAL OTHER EXPENSES |  |  |  | 597
|  | TOTAL PAL COST PROPOSAL |  |  | 9651.3
* This quote is valid for 120 days from date listed above.