## Sheet1
Soule Homestead |  |  | Step 2 application submitted by Nov. 1, 2013
CPA Budget, Funding, Timeline
Total project budget: |  | 57171
Note: All carpentry labor is estimated at $30 / hr ($240 / day per man)
Estimate Details House:
4000 | Chimney labor: |  | Re-point and reflash 2 red brick chimneys above 2nd floor roof.
( Mason & Helper: 8 days @ $500 / Day 8 X 500 = 4,000)
200 |  |  | Materials $200
11200 | Roofing labor & material |  | Strip / dispose and replace 2800 square feet of asphalt roofing.
(Material and labor (including insurance) $400 / sq =$11,200)
3360 | Trim & gutter work labor |  | (2 Carpenters 7 days = 14 x 240 = $3,360)
700 | Material |  | Materials $700 |  | Note: for wood gutter add $2,500
2400 | Window labor |  | 34 windows total (20 need some work)
100 | Material |  | (Average 4 hours / window @ $30 hr = $120 x 20 =$2,400)
720 | Shutter labor |  | Labor to remove and replace 8 sets of shutters 3 hr / set = 24 hrs x $30 = $720
2800 | Material |  | 8 sets @ $350 set composite or wood = $2,800
2400 | Siding labor |  | Strip and re-side north walls 800 square feet pre stained white cedar extras
(2 carpenters 5 days = 10 X 240 = $2,400)
3600 | Material |  | Material 8 sq shingles x $430 = 3,440 + nails and paper
1920 | Woodshed labor |  | Replace a section of sill & rebuild small doors
300 | Material |  | (2 carpenters 4 days = 8 X 240 = $1920)
33700 | Total
Estimate Details Barn:
4800 | Trim labor |  | Repair and / or replace exterior trim where needed
1000 | Material |  | (2 carpenters 10 days = 20 X 240 = $4,800)
4800 | Siding labor |  | Strip / dispose and re-side north walls 800 sq feet with unstained white cedar extras
(2 carpenters 10 days @ 480 / day = $4,800)
2400 | Material |  | 900 square feet white cedar extras @ $200 / sq ($1,800) + large vent, nails and paper
2160 | Window labor |  | Replace 18 windows |  |  | (2 hrs / unit x $30 = 60 X 18 =$1,080)
|  |  | Repair & reglaze 12, 6 over 6 sash |  |  | 3 hours each (36 x 30 = $1080)
6000 | Material |  | 20 windows @ $300 / unit =$6,000
21160 | Total
|  |  | 33700 | house
|  |  | 21160 | barn
|  |  | 54860 | sub total
Non roofing labor |  | 26560 | 2310.72 | Workmen's Comp Insurance 8.7% of $26,560
|  |  | 57170.72 | Total project estimated cost
Administrative costs to be absorbed by Soule Homestead
Timeline
Work will be started as soon as funding becomes available and will be continued until completed.